## Slide 1
RPA Weekly Status report
Summary – Progress this week
Add new Joiners to Group Scheme (API) ILHWB-1001 Tested API with Anya on Thursday (2h30mins). Bot is able to get a response from API when a new joiner has been created. There is an issue with the date format in excel where it cannot be passed through the API. Solution found but needs to be tested. Aged Debt Reminder Letters ILH-1002 Bot is 70% complete, waiting for final letter layout to be determined from Margaret Dunn Adjust letter format in PDF forms Split Billing Reminder Letters ILHWB-982 Some issues with Abobe while running bot in unattended state, these have been corrected. PDF Letters are now created and are password protected. Full testing with the Corporate team will be done on Monday
Next week
Add new Joiners to Group Scheme (API) ILHWB-1001 Correct date issue and test process, split response string to get policy number. Speak to Anya to allow for Employee Number to be entered via API, this is currently done manually but never documented to me during requirements gathering. Aged Debt Reminder Letters ILH-1002 Wait for letter layout clarification, create Editable PDF’s, finish bot development Split Billing Reminder Letters ILHWB-982 Test process with corporate team on Monday, adjust if needed Boston Science Reporting ILHWB-1139 Meet with Margaret Dunn for discussion to understand process Begin Macro development
Completed Projects |  | 
Name | Benefits | Benefits
List the items completed – include JIRA # |  | 
Workstream: Optimise
Project Name: Robotic Process Automation (RPA)
Project description: Implementing RPA to automate business processes
RPA Developer: Anthony Slator IT Lead: Gerard Coughlan Kanban: https://jirasrv:8443/secure/RapidBoard.jspa?rapidView=915
Date: w/e 08/10/2021
RAG | This Week’s RAG | Last Week’s RAG
Rationale |  | 
Upcoming initiatives |  | 
Name | JIRA # | Start Date
Cash Matching Invoices | ILHWB-989 | 26/07/2021
Cash Matching Remittance | ILHWB-990 | 03/08/2021
Aged Debt Reminder Letters | ILHWB-1002 | 29/09/2021
Split Billing Reminder Letters | ILHWB-982 | 05/08/2021
Add New Joiners to Group Schemes (API) | ILHWB-1001 | 12/08/2021
Actuarial Mass Lapse | ILHWB-987 | TBA
Boston Science Reporting | ILHWB-1139 | TBA