## Slide 1
RPA Weekly Status report
Summary – Progress this week
Add new Joiners to Group Scheme (API) ILHWB-1001 Tested process after corrections were made, still have an “Message cannot be understood” error. Too arrange a call with Anya for Monday Split Billing Reminder Letters ILHWB-982 Adobe Acrobat Pro has been installed on the VM Bot but is a different version to the one on my laptop Tested writing of letters in the bot and had to make changes to allow for the different version of Adobe Aged Debt Reminder Letters ILH-1002 Began bot development, had a call with Margaret Dunn to understand where Invoice Numbers will come from and letter format issues to be corrected. Fixed some bot issues that arose while I was on annual leave
Next week
Add new Joiners to Group Scheme (API) ILHWB-1001 Too arrange a call with Anya for Monday, test API upload Aged Debt Reminder Letters ILH-1002 Continue development of bot Adjust letter format in PDF forms Split Billing Reminder Letters ILHWB-982 Test process further before go live
Completed Projects |  | 
Name | Benefits | Benefits
List the items completed – include JIRA # |  | 
Workstream: Optimise
Project Name: Robotic Process Automation (RPA)
Project description: Implementing RPA to automate business processes
RPA Developer: Anthony Slator IT Lead: Gerard Coughlan Kanban: https://jirasrv:8443/secure/RapidBoard.jspa?rapidView=915
Date: w/e 01/10/2021
RAG | This Week’s RAG | Last Week’s RAG
Rationale |  | 
Upcoming initiatives |  | 
Name | JIRA # | Start Date
Cash Matching Invoices | ILHWB-989 | 26/07/2021
Cash Matching Remittance | ILHWB-990 | 03/08/2021
Aged Debt Reminder Letters | ILHWB-1002 | 29/09/2021
Split Billing Reminder Letters | ILHWB-982 | 05/08/2021
Add New Joiners to Group Schemes (API) | ILHWB-1001 | 12/08/2021
Actuarial Mass Lapse | ILHWB-987 | TBA
Boston Science Reporting | ILHWB-1139 | TBA